ENGE707 Assessment 3 — Step-by-Step Plan

Facial Feature Classification Challenge

One step at a time, in the order to actually do them — from registration to final submission.

Key dates: Kaggle sign-up due 2 October 2026 · Final report/submission due 25 October 2026.

Work through the steps in order. Each one builds on the last, so don't skip ahead to modelling before the dataset and pipeline steps are done.

Phase A — Registration & Setup  (now → 2 Oct)

- Join the Kaggle competition — open the private invitation link and click "Join Competition".

- Accept the competition rules — on Kaggle, when prompted.

- Submit the Microsoft Form — name, student ID, AUT email, Kaggle username, and the email used for Kaggle — due before 2 Oct.

- Create a GitHub repository — for this project and make your first commit (folder structure + a short README).

- Set up your Python environment — choose PyTorch or TensorFlow/Keras, and a GPU runtime such as Kaggle Notebooks or Google Colab.

- Download the data — train/ and test/ image folders, train_labels.csv, and sample_submission.csv.

- Verify the data — check the actual file counts in train/ and test/ match the CSV row counts, and scan for corrupted, duplicate, or unusually small/large images.

- Count images per class — from train_labels.csv, and plot the class distribution.

- Display sample images — a small grid (e.g. 4 images) from each of the 8 classes to visually confirm the labels look right.

- Write up Task 1 — draft the dataset exploration section of your report while it's fresh — problem description, class balance discussion, data quality notes.

Phase B — Preprocessing & Baseline  (3 – 9 Oct)

- Choose your input image size — matched to the model you'll use in Phase C (e.g. 224×224 for most ImageNet-pretrained CNNs).

- Decide normalisation — rescale pixel values consistently (e.g. [0,1] or ImageNet mean/std).

- Encode the 8 class labels — build a label map and its inverse.

- Create a stratified train/validation split — e.g. 80/20, preserving class proportions in both sets.

- Choose augmentation techniques — flips, small rotations, mild colour jitter — avoid crops aggressive enough to cut off the eye/nose/mouth feature itself.

- Build one shared data pipeline — a Dataset/generator that applies identical loading, resizing, and normalisation to train, validation, and test (augmentation only on train).

- Check for data leakage — confirm no image appears in more than one of train/validation/test.

- Build and train a baseline custom CNN — get something training end-to-end, even if accuracy is mediocre — this proves the pipeline works.

- Make a first throwaway Kaggle submission — using the baseline model, purely to confirm your prediction-to-CSV pipeline matches sample_submission.csv.

Phase C — Transfer Learning & Training Strategy  (10 – 16 Oct)

- Select a transfer-learning architecture — e.g. ResNet18/34, EfficientNet-B0, or MobileNetV2 — and justify the choice in your notes.

- Replace the final layer — swap in an 8-unit output layer for softmax / cross-entropy loss.

- Train in two stages — freeze the pretrained backbone and train the new head first, then unfreeze and fine-tune later layers at a lower learning rate.

- Log training and validation accuracy/loss every epoch — and plot both curves together.

- Diagnose overfitting or underfitting — from the curves, and apply fixes as needed — dropout, weight decay, more augmentation, early stopping, learning-rate scheduling.

- Iterate on hyperparameters — learning rate, batch size, epochs — keeping a simple log of (setup → validation accuracy) for each attempt.

Phase D — Final Evaluation & Kaggle Submission  (17 – 21 Oct)

- Evaluate on the validation set — overall accuracy, precision/recall/F1 per class, and a confusion matrix.

- Run inference on the full test set — through the same preprocessing pipeline used for training.

- Format the submission file — exactly matching sample_submission.csv (image_id, class), and check the row count is 29,443.

- Submit to Kaggle and record the leaderboard score — keep a screenshot as evidence.

- Compare validation accuracy to the Kaggle score — note and explain any gap.

- Analyse misclassifications — use the confusion matrix to find which classes get confused most often.

- Run at least one deliberate comparison experiment — e.g. a different backbone or class-weighted loss for the Eye-class imbalance, and compare it to your main model.

Phase E — Report, Reproducibility & Submission  (22 – 25 Oct)

- Write the full report — 3,000–3,500 words, covering dataset, preprocessing, model, training strategy, evaluation, Kaggle results, analysis, and improvement strategies.

- Attach source code or notebook — with clear comments and instructions to reproduce your pipeline.

- Include the final Kaggle submission file — plus your Kaggle username and leaderboard evidence.

- Add references — for every external library, pretrained model, paper, or tutorial used.

- Run your Turnitin check — confirm similarity is 20% or below.

- Proofread and compile the final submission package — report, code, dataset/reproduction instructions, GitHub link, Kaggle evidence.

- Prepare for the demo/viva — be ready to explain your dataset, preprocessing, model, pipeline, results, and improvement ideas.

# Ongoing throughout every phase

- At least 2 meaningful GitHub commits per week — spread out, not bunched at the end.

- Complete each lab as it's assigned and link it explicitly to your project progress.

- Keep your experiment log updated every time you change the model or training setup.